## Dec 2020
Annexure-31
RSETI - STATUS OF LAND ALLOTMENT IN THE STATE OF PUNJAB AS ON 31.12.2020
Sr.No. | District | From where functioning | Whether land has been allocated | Whether possession of land has taken (if not, reasons thereof) | Whether Building Plan has been got approved from the competent authority | Whether construction has started | Tentative Date for completion of construction, if commenced. | Amount of Charges paid for CLU, EDC etc.
1 | Amritsar | Mallian | Yes | Yes | Yes | NA | NA | Paid
2 | Barnala | Khudi Kalan | Yes | Yes | Yes | Yes | 44348 | Rs 5000/-
3 | Bathinda | Red Cross Bhawan, Bathinda | Yes | Yes | Yes | No | NA | Rs. 348900.00
4 | Faridkot | VPO Chahal, Faridkot | Yes | Yes | Yes | Aleady Functioning w.e.f 09-06-2016 | Aleady Functioning w.e.f 09-06-2016 | _______
5 | Fatehgarh Sahib | Opp. BSNL exchange, Inside BDPO Office Sirhind, Fatehgarh Sahib | Yes | Yes | Yes | Yes | 31-03-2021 | Lease Rent Rs. 40200.00 P.A.
6 | Ferozepur | Own Bulding | Yes | Yes | yes | yes |  | Paid
7 | Gurdaspur | Not Functioning | __________ | __________ | __________ | __________ | __________ | __________
8 | Hoshiarpur | Rented building. Provided by Distt. Administration (Zilla Parishad), Hoshiarpur whch too is inadequate. Paying rent of Rs.8000/- per month | Fresh land not allocated so far | NOT APPLICABLE | NOT APPLICABLE | NOT APPLICABLE | N.A. | NA
9 | Jalandhar | PLOT NO. 7/235 NEW VIJAY NAGAR JALANDHAR | Punjab Govt has Allotted Alternative Land for own campus of RUDSET in Bastidanishmanda, Jalandhar. | with the support of District Administration, demarcation of allotted Land has been done. As per the Demarcation report of the land, there are some residential constructions by some natives of the area. which occupied 15% to 20% portion of the particular land | N A | NO | no | No
10 | Kapurthala | Pb. Govt. Building/Zila Parishad Building | Yes | Yes | Yes | Yes | January.2021 | _______
11 | Ludhiana | Rural Self Employement Training Institute,Ayali Khurd Dana Mandi,Humbran road,Ludhiana | yes | yes | yes | completed | NA | ________
12 | Mansa | VILLAGE CHAKERIAN,DISTRICT MANSA PIN 151505 | Yes | Yes | Yes | Yes | construction of building is completed & We shifted into our new building AT VILLAGE CHAKERIAN IN May-2020 | NIL
13 | Moga | PSB RSETI DUNNEKE MOGA | YES | YES | YES | COMPLETED | NA | __________
14 | Sri Muktsar Sahib | OWN | YES | YES | YES | COMPLETED | _______ | _______
15 | Pathankot | Not functioning | NO | NO | No | No | NA | NIL
16 | Patiala | Village-Jassowal,Bhadson Road,Patiala | Yes(Lease deed has been executed) | Yes | The map has been got approved from STP | yes | Construction completed and RSETI shifted to new building on 07.10.2016 | Necessary processing fee of Rs-5000/- for issuance of CLU certificate has already been deposited with District town planner
17 | Rupnagar | Own Building at VPO Rangilpur Distt Ropar 140108 | Yes | Yes | Yes | Yes | Completed | Nil
18 | Sangrur | OWN BUILDING | YES | YES | YES | CONSTRUCION HAS BEEN COMPLETED AND BUILDING INAUGURATED DATED 29/08/2016 | RSETI IS FUNCTIONING IN ITS OWN BUILDING | NIL
19 | SAS Nagar | Plot No.1, Vikas Bhawan, Sector 62,Mohali | No | ___________ | ___________ | ___________ | ___________ | ___________
20 | Tarn Taran | Not Functioning | ___________ | ___________ | ___________ | ___________ | ___________ | ___________
21 | Fazilka | Not Functioning | ___________ | ___________ | ___________ | ___________ | ___________ | ___________
22 | Pathankot | Not Functioning | ___________ | ___________ | ___________ | ___________ | ___________ | ___________
SLBC Punjab