## SEP 2020
Annexure - 36
RSETI - STATUS OF LAND ALLOTMENT IN THE STATE OF PUNJAB : SEP 2020
S. No. | District | From where functioning | Whether land has been allocated | Whether possession of land has taken (if not, reasons thereof) | Whether Building Plan has been got approved from the competent authority | Whether construction has started | Tentative Date for completion of construction, if commenced. | Amount of Charges paid for CLU, EDC etc.
1 | Amritsar | Mallian | Yes | Yes | Yes | Completed | _______ | Paid
2 | Bathinda | Red Cross Bhawan, Bathinda | Yes | Yes | Under Process | No | ______ | Rs. 348900.00
3 | Barnala | Khuddi Kalan | Yes | Yes | Yes | Yes | June. 2021 | Rs. 5000/-
4 | Faridkot | VPO Chahal, Faridkot | Yes | Yes | Yes | Aleady Functioning w.e.f 09-06-2016 | ______ | ______
5 | Fatehgarh Sahib | BDPO Office Sirhind | Yes | Yes | Yes | Yes | 31.12.2020 | ______
6 | Firozpur | Ratol Bet | Yes | Yes | Yes | Yes | 31.12.2013 | Rs. 172000.00
7 | Gurdaspur | Not functioning | ______ | ______ | ______ | ______ | ______ | ______
8 | Hoshiarpur | Rented building. Provided by Distt. Administration (Zilla Parishad), Hoshiarpur whch too is inadequate. Paying rent of Rs.8000/- per month | No | ______ | ______ | ______ | ______ | ______
9 | Jalandhar | PLOT NO. 7/235 NEW VIJAY NAGAR JALANDHAR | Punjab Govt has Allotted Alternative Land for own campus of RUDSET in Bastidanishmanda, Jalandhar. | with the support of District Administration, demarcation of allotted Land has been done. | ______ | NO | ______ | No
10 | Kapurthala | Pb. Govt. Building/Zila Parishad Building | Yes | Yes | Yes | Yes | 2020-11-01 | _______
11 | Ludhiana | Ayali Khurd Dana Mandi,Humbran road,Ludhiana | Yes | Yes | Yes | completed | ______ | _______
12 | Mansa | VILLAGE CHAKERIAN,DISTRICT MANSA PIN 151505 | Yes | Yes | Yes | Yes | 2020-05-01 | NIL
13 | Moga | OWN PREMISES | Yes | Yes | Yes | COMPLETED | OWN PREMISES | _______
14 | SAS Nagar | Plot No. 1, Vikas Bhawan ,Sectoe 62, Mohali . | No | ______ | ______ | ______ | ______ | _______
15 | Muktsar Sahib | OWN PREMISESS | Yes | Yes | Yes | COMPLETED | ______ | ______
16 | SBS Nagar | No | No | ______ | ______ | ______ | ______ | ______
17 | Patiala | Village-Jassowal,Bhadson Road,Patiala | Yes(Lease deed has been executed) | Yes | The map has been got approved from STP | Yes | completed on 07.10.2016 | Necessary processing fee of Rs-5000/- for issuance of CLU certificate has already been deposited with District town planner
18 | Rupnagar | Panchayat Bhawan Ropar | Yes | Yes | Yes | Yes | Completed | NIL
19 | Sangrur | OWN BUILDING | Yes | Yes | Yes | CONSTRUCION HAS BEEN COMPLETED AND BUILDING INAUGURATED DATED 29/08/2016 | RSETI IS FUNCTIONING IN ITS OWN BUILDING | NIL
20 | Tarn Taran | Not functioning | _______ | _______ | _______ | _______ | _______ | _______
21 | Fazilka | Not functioning | _______ | _______ | _______ | _______ | _______ | _______
22 | Pathankot | Not functioning | _______ | _______ | _______ | _______ | _______ | _______
SLBC Punjab

## Sheet1
14 | SAS Nagar | Plot No. 1, Vikas Bhawan ,Sectoe 62, Mohali . | No | ______ | ______ | ______ | ______ | _______
15 | Muktsar Sahib | OWN PREMISESS | Yes | Yes | Yes | COMPLETED | ______ | ______
16 | SBS Nagar | No | No | ______ | ______ | ______ | ______ | ______
17 | Patiala | Village-Jassowal,Bhadson Road,Patiala | Yes(Lease deed has been executed) | Yes | The map has been got approved from STP | Yes | completed on 07.10.2016 | Necessary processing fee of Rs-5000/- for issuance of CLU certificate has already been deposited with District town planner
18 | Rupnagar | Panchayat Bhawan Ropar | Yes | Yes | Yes | Yes | Completed | NIL
19 | Sangrur | OWN BUILDING | Yes | Yes | Yes | CONSTRUCION HAS BEEN COMPLETED AND BUILDING INAUGURATED DATED 29/08/2016 | RSETI IS FUNCTIONING IN ITS OWN BUILDING | NIL
20 | Tarn Taran | Not functioning | _______ | _______ | _______ | _______ | _______ | _______
21 | Fazilka | Not functioning | _______ | _______ | _______ | _______ | _______ | _______
22 | Pathankot | Not functioning | _______ | _______ | _______ | _______ | _______ | _______