## Functional
Annexure- 27
RSETI - STATUS OF LAND ALLOTMENT IN THE STATE OF PUNJAB AS ON 31.12.2021
Part A (Functioning without any issue) -14
Sr.No. | District | From where functioning | Sr.No. | District | From where functioning | Sr.No. | District | From where functioning
1 | AMRITSAR Lead Bank- PNB | MALLIAN | 6 | FEROZEPUR Lead Bank- PNB | OWN BULDING | 11 | SRI MUKTSAR SAHIB Lead Bank- SBI | OWN
2 | BARNALA Lead Bank- SBI | KHUDI KALAN | 7 | KAPURTHALA Lead Bank- PNB | PB. GOVT. BUILDING/ZILA PARISHAD BUILDING | 12 | PATIALA Lead Bank- SBI | VILLAGE-JASSOWAL,BHADSON ROAD,PATIALA
3 | BATHINDA Lead Bank- SBI | RED CROSS BHAWAN, BATHINDA | 8 | LUDHIANA Lead Bank- PSB | RURAL SELF EMPLOYEMENT TRAINING INSTITUTE,AYALI KHURD DANA MANDI,HUMBRAN ROAD,LUDHIANA | 13 | ROPAR Lead Bank- UCO | OWN BUILDING AT VPO RANGILPUR DISTT ROPAR 140108
4 | FARIDKOT Lead Bank- PSB | VPO CHAHAL, FARIDKOT | 9 | MANSA Lead Bank- SBI | VILLAGE CHAKERIAN,DISTRICT MANSA PIN 151505 | 14 | SANGRUR Lead Bank- SBI | OWN BUILDING
5 | FATEHGARH SAHIB Lead Bank- SBI | OPP. BSNL EXCHANGE, INSIDE BDPO OFFICE SIRHIND, FATEHGARH SAHIB | 10 | MOGA Lead Bank- PSB | PSB RSETI DUNNEKE MOGA
Part B (Functioning and having issues) - 3
Sr.No. | District | From where functioning | Whether land has been allocated | Whether possession of land has taken (if not, reasons thereof) | Whether Building Plan has been got approved from the competent authority | Whether construction has started | Tentative Date for completion of construction, if commenced. | Amount of Charges paid for CLU, EDC etc.
1 | JALANDHAR Lead Bank- UCO | PLOT NO. 7/235 NEW VIJAY NAGAR JALANDHAR | NO | PUNJAB GOVT HAS ALLOTTED ALTERNATIVE LAND FOR OWN CAMPUS OF RUDSET IN BASTIDANISHMANDA, JALANDHAR.WITH THE SUPPORT OF DISTRICT ADMINISTRATION, DEMARCATION OF ALLOTTED LAND HAS BEEN DONE. AS PER THE DEMARCATION REPORT OF THE LAND, THERE ARE SOME RESIDENTIAL CONSTRUCTIONS BY SOME NATIVES OF THE AREA. WHICH OCCUPIED 15% TO 20% PORTION OF THE PARTICULAR LAND |  | NO | NOT STARTED | NA
2 | HOSHIARPUR Lead Bank- PNB | RENTED BUILDING. PROVIDED BY DISTT. ADMINISTRATION (ZILLA PARISHAD), HOSHIARPUR WHICH TOO IS INADEQUATE. PAYING RENT OF RS.8000/- PER MONTH | NO | INITIALLY THE DISTRICT ADMINISTRATION ALLOTTED THE LAND APPX. 1 ACRS AT NEAR BY R.C CAMP HOSHIARPUR ON CHANDIGARH HIGHWAY BUT THE CIRCLE OFFICE RETURNED THE POSSESSION OF LAND TO ADMINISTRATION DUE TO AVAILABLE OF MANY TREES IN THE ALLOTTED LAND & NGT TRIBUNAL NOT ALLOWED TO REMOVE THE TREES. HENCE, THE MAP OF RSETI WAS NOT POSITION TO EXECUTE FOR CONSTRUCTION OF BUILDING AS PLANNED FOR R.SETI. AS PER LDM OFFICE NEW ADC HAS ASSURED THE LEAD BANK TO ALLOCATE LAND SOON. |  | NO | NOT STARTED | NA
3 | SAS NAGAR Lead Bank- PNB | PLOT NO.1, VIKAS BHAWAN, SECTOR 62,MOHALI | NO | PNB CRDT, HO PSFID VIDE LETTER PSFI/RSETI/BOARD-30THATR//17-18 DATED 14TH MAR 2018, DURING 30THE BOARD MEETING OF PNB CRDT HELD ON 30.01.2018 HAS DROPPED THE CONSTRUCTION OF THE RSETI.

## Non Functional
Part C (Non-Functional with issues)- 5
Sr.No. | District | Issues
1 | PATHANKOT Lead Bank- PNB | ONE ACRE LAND FOR CONSTRUCTION OF RSETI WAS ACQUIRED AND LEASE DEED WAS EXECUTED ON 27.12.2016. BUT DUE TO NON COMPLETION OF FORMALITIES / PROCEDURE OF RSETI THE BOARD OF PNB DROPPED THE PROPOSAL FOR CONSTRUCTION OF BUILDING OF RSETI AT PATHANKOT . GRAM PANCHAYAT CANCELLED THE LEASE ON 06.11.2019. AFTER THAT ONE ROOM WAS ALLOTED BY DC PATHANKOT FOR RUNNING OF RSETI BUT THE SPACE WAS VERY LESS FOR RUNNING OF RSETI, HENCE THE ROOM WAS ALSO SURRENDERED TO THE DISTRICT ADMINISTRATION .
2 | GURDASPUR Lead Bank- PNB | MATTER WAS TAKEN UP WITH DISTRICT ADMINISTRATION FOR GETTING TEMPORARY ACCOMMODATION FOR STARTING RSETI. IN THIS REGARD THE DISTRICT ADMINISTRATION, I.E ADC (D) HAS DECLINED TO PROVIDE RENT FREE ACCOMMODATION FOR SETTING UP OF RSETI AND ADVISED US TO MAKE OUR OWN ARRANGEMENT FOR IT. FURTHER, JOINT DEVELOPMENT COMMISSIONER PUNJAB ALSO ADVISED THAT BANK SHOULD BE ASKED TO PAY A REASONABLE RENT, AS BEING PAID IN OTHER CENTRES LIKE MOHALI. AS SUCH MATTER BE TAKEN UP WITH HIGHER AUTHORITIES.
3 | TARN TARAN Lead Bank- PNB | DISTT AUTHORITIES HAVE AGREED TO PROVIDE 6 KANALS OF LAND ON 33 YEARS LEASE AT VILLAGE USMA BLOCK NAUSHERA PANNUAN. THE REVENUE PAPERS OF THE SAID LAND ARE BEING TAKEN FROM THE CONCERNED SARPANCH OF THE VILLAGE AND AFTER GETTING ALL THE PAPERS A PROPOSAL TO SET UP TO RSETI WILL BE SUBMITTED TO PNB HO THROUGH CIRCLE OFFICE. AFTER RESPONSE FROM PNB HO THE MATTER WILL BE TAKEN UP WITH THE DISTT ADMINISTRATION TO PROVIDE TEMPORARY INFRASTRUCTURE FOR STARTING THE FUNCTIONING OF RSETI MEANWHILE.
4 | FAZILKA Lead Bank- PNB | LDM FAZILKA INFORMED THAT SPACE/ACCOMMODATION IS NOT PROVIDED BY CONCERNED AUTHORITY. A LETTER DATED 09-01-2020 IS SENT TO DEPUTY COMMISSIONER, FAZILKA FOR PROVIDING ACCOMMODATION BUT IT IS PENDING TILL DATE
5 | SBS NAGAR Lead Bank- PNB | ON THE BASIS OF LDM LETTER TO CIRCLE OFFICE KAPURTHALA DT. 16.10.2020, CIRCLE OFFICE HAD ALREADY FORWARDED THE MATTER TO OUR HEAD OFFICE FOR SETTING UP RSETI IN DISTRICT SBS NAGAR. HEAD OFFICE ASKED FOR FRESH REQUEST OF RSETI WITH PHOTOGRAPHS OF BUILDING.