## Functional
Annexure- 37
RSETI - STATUS OF LAND ALLOTMENT IN THE STATE OF PUNJAB AS ON 30.09.2022
Part A (Functioning without any issue) -14
Sr.No. | District | From where functioning | Sr.No. | District | From where functioning | Sr.No. | District | From where functioning
1 | AMRITSAR Lead Bank- PNB | OWN BUILDING | 6 | FEROZEPUR Lead Bank- PNB | OWN BULDING | 11 | SRI MUKTSAR SAHIB Lead Bank- SBI | OWN BUILDING
2 | BARNALA Lead Bank- SBI | OWN BUILDING | 7 | KAPURTHALA Lead Bank- PNB | OWN BUILDING | 12 | PATIALA Lead Bank- SBI | VILLAGE-JASSOWAL,BHADSON ROAD,PATIALA
3 | BATHINDA Lead Bank- SBI | RED CROSS BHAWAN, BATHINDA (At present in Rented Building at Red Cross Bhawan. Construction of Compound wall is in progress.) | 8 | LUDHIANA Lead Bank- PSB | OWN BUILDING | 13 | ROPAR Lead Bank- UCO | OWN BUILDING
4 | FARIDKOT Lead Bank- PSB | OWN BUILDING | 9 | MANSA Lead Bank- SBI | OWN BUILDING | 14 | SANGRUR Lead Bank- SBI | OWN BUILDING
5 | FATEHGARH SAHIB Lead Bank- SBI | OPP. BSNL EXCHANGE, INSIDE BDPO OFFICE SIRHIND, FATEHGARH SAHIB | 10 | MOGA Lead Bank- PSB | OWN BUILDING
Part B (Functioning and having issues) - 3
Sr.No. | District | From where functioning | Whether land has been allocated | Whether possession of land has taken (if not, reasons thereof) | Whether Building Plan has been got approved from the competent authority | Whether construction has started | Tentative Date for completion of construction, if commenced. | Amount of Charges paid for CLU, EDC etc.
1 | JALANDHAR Lead Bank- UCO | PLOT NO. 7/235 NEW VIJAY NAGAR JALANDHAR | NO | At present in the rented building. Land has been allotted. Compound wall has been constructed. Map/sketch along with the estimated cost of the new building has been sent to the honorable President, RUDSETI Sir for approval. Once the approval comes, construction work shall be started after getting requisite approval from the Municipal Authorities. SDR Punjab State has already instructed the Project Contractor to start the work immediately after getting the requisite approvals from various authorities. |  | NO | NOT STARTED | NA
2 | HOSHIARPUR Lead Bank- PNB | RENTED BUILDING. PROVIDED BY DISTT. ADMINISTRATION (ZILLA PARISHAD), HOSHIARPUR WHICH TOO IS INADEQUATE. PAYING RENT OF RS.8000/- PER MONTH | NO | At present in the rented building. SDR Punjab State along with Director Rseti Hoshiarpur met ADC Development, Hoshiarpur on May 11, 2022 and requested him to allot One Acre of Land in the nearby areas. The District Administration has taken a decision to allot one Acre of Land at village Chabbewal. |  | NO | NOT STARTED | NA
3 | SAS NAGAR Lead Bank- PNB | PLOT NO.1, VIKAS BHAWAN, SECTOR 62,MOHALI | NO | At present in rented building. Dy. CEO, Zila Parishad has asked BDPO to allot One Acre of Land to PNB. LDM PNB has written to BDPO on May 04, 2022 to allot us One Acre of Land at suitable place adjoining Mohali. District Administration has given us three four options which shall be visited by LDM, Director Rseti Mohali and State Director Punjab for Rsetis on November 04, 2022 and shall request the Sponsored Bank to take a final call. Further, SDR Punjab State had requested ADC Development to provide us two big rooms so that Rseti Mohali can conduct training programs in campus.

## Non Functional
Part C (Non-Functional with issues)- 5
Sr.No. | District | Issues
1 | PATHANKOT Lead Bank- PNB | SDR Punjab State along with LDM visited ADC Development Pathankot and requested him to allot us One Acre of Land and four to five rooms for temporary accommodation to start the RSETI. The matter was put on hold for want of requisite permission from the MORD, GOI, as advised by our Controlling Office, NACER, Bengaluru.
2 | GURDASPUR Lead Bank- PNB | SDR Punjab State along with LDM PNB met DC Gurdaspur and they have offered One Acre of Land at Zila Parishad Batala and One Big Hall and two rooms for temporary accommodation to start the RSETI. The matter was put on hold for want of requisite permission from the MORD, GOI, as advised by our Controlling Office, NACER, Bengaluru.
3 | TARN TARAN Lead Bank- PNB | SDR Punjab State along with LDM PNB met ADC Development Tarntaran and requested them to allot One Acre of Land and four to five rooms for temporary accommodation to start the RSETI. The matter was put on hold for want of requisite permission from the MORD, GOI, as advised by our Controlling Office, NACER, Bengaluru.
4 | FAZILKA Lead Bank- PNB | SDR Punjab State along with LDM PNB shall meet ADC Development in the first week of June 2022 with a request to allot One Acre Land and four to five rooms for temporary accommodation to start the RSETI. The matter was put on hold for want of requisite permission from the MORD, GOI, as advised by our Controlling Office, NACER, Bengaluru.
5 | SBS NAGAR Lead Bank- PNB | The matter was put on hold for want of requisite permission from the MORD, GOI, as advised by our Controlling Office, NACER, Bengaluru.
6 | MALERKOTLA | SDR Punjab State along with LDM SBI Malerkotla shall meet ADC Development of May 25, 2022 with a request to allot One Acre of Land for construction of Rseti and four to five rooms for temporary accommodation to start the RSETI. The proposal shall be placed in the ensuing SLBC Punjab Meeting by SBI for approval